## Sheet1
DailyNeeds EmployeePortal High Level Timelines | FY-22
| Q4 |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
| Nov | Dec | Jan | Feb | Mar | April | May | June | July | Aug | Sept | Oct | Nov | Dec
Analysis and Planning | bar: Q4 Nov
Requirment Gathering | bar: Q4 Dec to Q1 Jan
Design and Prototyping | bar: Q1 Feb to Q1 Mar
Software Development | bar: Q2 April to Q3 July
QA Testing | bar: Q3 Aug
UAT Testing | bar: Q3 Sept
Deployment | bar: Q4 Oct
Maintainance and Updates | bar: Q4 Nov to Q4 Dec